# Broadalbin-Perth High School Signage Rename Cost Estimate

## Executive summary

Using the official website for Broadalbin-Perth Central School District[1], district PDFs, athletics pages, the attached image, official Town of Broadalbin permit documents, local sign-vendor capability pages, and current commercial sign-pricing guides, the most defensible planning budget for a practical physical-sign rename at the 100 Bridge Street campus in Broadalbin[2] is about $54,825 mid-case, with a low-to-high range of about $26,975 to $116,900, before any carved-masonry discoveries or major electrical upgrades. The main cost drivers are the entrance façade letters, a probable roadside monument sign, campus wayfinding, athletic field identifiers that explicitly use "BPHS," and a likely interior office/door-sign refresh. [3]

A narrower, high-confidence scope - replacing only the items directly visible or explicitly named in official materials - lands around $10,675 low / $20,425 mid / $38,000 high. A broader campus-standardization scope - which is what most districts actually end up buying once procurement starts - is what pushes the budget toward the mid-case number above. If an existing monument can be refaced instead of rebuilt, and if the district limits the project to only the signs that literally contain the old school name or acronym, the total could compress materially. If the district chooses illuminated channel letters, rebuilds the monument entirely, or discovers carved stone/brick lettering or scoreboard headers with the old name, the cost can move well above the midpoint. [4]

The official district materials already show multiple active naming variants, which is a scope-risk all by itself. I found at least these variants on official district pages and district PDFs: "Broadalbin-Perth High School," "Broadalbin-Perth Jr./Sr. High School," "Broadalbin-Perth Secondary Campus," "Broadalbin-Perth Junior Senior High School," "Broadalbin-Perth Senior High School," plus the abbreviations "BPHS" and "B-P High School." Before any fabrication starts, the district should decide exactly which final public-facing name, acronym, and sub-brand rules will be used for exterior signs, interior room signs, athletics, and publications. [5]

| Scenario | Low | Mid | High | What it means |
| --- | --- | --- | --- | --- |
| High-confidence rename only | $10,675 | $20,425 | $38,000 | Main entrance letters, counseling office, lecture hall, and the two baseball-field identifiers explicitly referenced online. |
| Practical campus rename program | $26,975 | $54,825 | $116,900 | Adds probable monument sign, wayfinding, parking signs, lobby sign, ADA/door-sign allowance, banners/flags, and plaque allowance. |
| Potential carved-masonry adder | +$7,500 | +$18,000 | +$35,000 | Use only if the field inventory finds carved stone/brick lettering or a monument base that cannot be economically refaced. |

## Verified naming inventory

Only one physical sign is directly confirmed by the attached image - the main brick-facade building name band. Everything else below is either explicitly named on official district pages or is a high-probability physical-sign implication of those official text strings.

| Current wording found online | Where it appears | Physical-sign implication |
| --- | --- | --- |
| BROADALBIN-PERTH HIGH SCHOOL | High school home page branding and the attached image of the façade. [6] | Confirmed exterior main entrance sign. |
| Broadalbin-Perth Jr./Sr. High School | District home page events and "Visit Us" page. [7] | Likely roadside monument sign, event wayfinding, parking, and campus directories. |
| Broadalbin-Perth Secondary Campus | Official page titles and section labeling. [8] | Likely campus-level directory copy and internal wayfinding copy. |
| Broadalbin-Perth Junior Senior High School | Curriculum page text. [9] | Possible printed sign family or older room/directory naming. |
| Broadalbin-Perth Senior High School | Course progressions and curriculum guide PDFs. [10] | Possible older plaques, office signs, legacy print panels, or donor signage. |
| B-P High School / BPHS | News items and athletics schedule. [11] | Athletic field signs, lecture hall signs, banner copy, parking signs, room plaques. |
| Broadalbin-Perth High School Counseling Office | Counseling page. [12] | High-confidence interior office/door sign. |
| BPHS Lecture Hall / High School Lecture Hall | Budget-hearing and graduation stories. [13] | High-confidence interior room plaque or wayfinding panel. |
| BPHS Varsity Baseball Field / BPHS JV Baseball Field | Athletics schedule. [14] | High-confidence athletic field identification panels. |
| Patriot Field | Capital-project athletic-facilities story. [15] | Athletic-complex sign or scoreboard header may need attention only if the school rename also changes related branding or if the sign includes the school name elsewhere. |

## Cost model by sign type

The table below shows the component build-up the itemized spreadsheet uses. These are planning estimates, not quotes. They include removal/demolition, fabrication/materials, installation, electrical, permits/inspections, structural/engineering, painting/patching, disposal, and contingency.

| Sign type | Typical materials / condition assumed | Component build-up by sign type | Typical total |
| --- | --- | --- | --- |
| Building-mounted dimensional letters | 18"-24" aluminum or fabricated-metal letters, pin-mounted over main entrance; base case assumes non-illuminated like-for-like replacement. | Removal $0.8k/$1.5k/$3.0k; fabrication $3.5k/$5.5k/$12.0k; installation $2.0k/$3.5k/$6.0k; electrical $0/$0.5k/$3.0k; permits $0.15k/$0.30k/$0.60k; engineering $0/$0.5k/$1.5k; patch/paint $0.5k/$1.2k/$2.5k; disposal $0.15k/$0.30k/$0.8k; contingency $1.5k/$3.0k/$3.5k. Basis: official façade wording, 18"-24" aluminum-letter pricing, and channel/dimensional-letter guides. [16] | $8.6k/$16.3k/$29.9k |
| Freestanding monument sign | 4' x 8' to 5' x 10' face, aluminum/composite panel on existing or rebuilt masonry/EPS/brick base; static, not digital. | Removal $0.5k/$1.5k/$4.0k; fabrication $5.0k/$9.0k/$18.0k; install/foundation $2.0k/$4.0k/$8.0k; electrical $0/$0.5k/$4.0k; permits $0.15k/$0.30k/$0.80k; engineering $0.5k/$1.2k/$3.0k; patch/site $0.2k/$0.6k/$1.5k; disposal $0.15k/$0.4k/$1.0k; contingency $1.2k/$2.4k/$6.0k. Basis: monument-sign cost guides and school custom-building-ID panels. [17] | $9.7k/$19.9k/$46.3k |
| Stone/brick carved lettering | Not observed online. Use only if the field walk finds carved or deeply incised school-name lettering that cannot be patched cleanly. | Removal/cap $0.5k/$2.0k/$5.0k; fabricate new overlay/veneer/panel $4.0k/$9.0k/$18.0k; install $2.0k/$4.0k/$6.0k; permits $0.15k/$0.30k/$0.80k; engineering $0.5k/$1.5k/$3.0k; patch/masonry repair $0.5k/$1.5k/$4.0k; disposal $0.15k/$0.30k/$0.80k; contingency $0.7k/$1.9k/$3.4k. Basis: monument and carved/sandblasted sign ranges. [18] | $7.5k/$18.0k/$35.0k |
| Exterior wayfinding and parking signs | .080 aluminum campus signs, reflective aluminum parking signs, post kits, basic concrete footings. | For larger campus wayfinding: panel/post package $0.38k-$1.22k each before installation; installed campus-quality allowance $0.65k/$1.05k/$1.70k each. For smaller parking signs: installed allowance $0.175k/$0.275k/$0.450k each. Basis: School Fix, Elements, parking-sign pricing, and school-sign installation benchmarks. [19] | See item table |
| Athletic field signs | 3' x 6' aluminum building-ID style panels, fence panels, or scoreboard headers. | Removal $0.1k/$0.2k/$0.5k; fabrication $0.4k/$0.8k/$1.6k; installation $0.3k/$0.6k/$1.2k; electrical $0/$0/$4.0k only if a lit scoreboard/header is involved; permits $0/$0.1k/$0.3k; contingency folded into row totals. Basis: school custom-sign pricing and athletics field naming evidence. [20] | $0.9k/$1.8k/$3.5k for a typical static field ID panel; more for scoreboard/header work. |
| Interior lobby signs | Acrylic or metal wall logo sign, typically 24" x 48" to 36" x 60". | Fabrication $0.3k/$0.8k/$2.0k; installation $0.2k/$0.5k/$1.0k; patching/contingency balance the rest. Basis: acrylic/logo sign retail benchmarks and local vendors with interior-sign capability. [21] | $0.7k/$1.6k/$4.0k |
| ADA, classroom, and office door signs | Engraved plastic, acrylic, aluminum-frame insert signs, and New York-compliant tactile/Braille signs where required. | Per-sign installed allowance $75/$130/$240 for a mixed package. Basis: office-sign and ADA-sign product pricing. [22] | Package total depends on count |
| Banners, pole banners, and school-branded flags | 16 oz vinyl banners, pole-banner hardware, custom logo flags. Government flags are excluded because a school rename usually does not affect them. | Banner / pole-banner units $129+ plus hardware; working installed allowance $250/$450/$750 each. Basis: School Fix school-banner and pole-banner pricing. [23] | See item table |
| Plaques | Bronze or aluminum cast plaque, roughly 18" x 24". | Fabrication $0.2k/$0.8k/$2.2k; installation $0.1k/$0.2k/$0.4k; patching, disposal, contingency balance the rest. Basis: bronze-plaque pricing ranges. [24] | $0.4k/$1.2k/$3.0k |

The official Town of Broadalbin documents support keeping separate allowances for permits and engineering. The town's permit information says permits are required for construction, alteration, removal, relocation, demolition, and electrical installation; the permit fee schedule shows a $50 minimum fee and a $50 demolition fee on the published town form; and the application states that projects over $20,000 require stamped plans. I did not locate an official online sign-fee schedule for the Village of Broadalbin, so the permit numbers in this report should be treated as a fee floor plus local-allowance placeholder until the jurisdiction is confirmed. [25]

## Detailed cost spreadsheet

The spreadsheet below prices physical signage only. It does not include website edits, stationery, apparel, vehicle graphics, printed handbooks, or scoreboard software changes. "Suggested new wording" is left as Unspecified because no final renamed school name was provided.

| Sign item | Confidence | Current wording | Suggested new wording | Est. size / likely material | Qty. | Unit cost L/M/H | Labor hours | Total cost L/M/H | Basis / notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main entrance façade name band | High | BROADALBIN-PERTH HIGH SCHOOL | Unspecified final school name | ~34'-40' overall; 25 individual 18"-24" aluminum dimensional letters over brick band | 1 | $8,600 / $16,300 / $29,900 | 30-55 | $8,600 / $16,300 / $29,900 | Official wording is on the school site, and the attached image confirms a physical exterior sign. Material basis comes from 18"-24" aluminum-letter pricing plus dimensional/channel-letter guides. [16] |
| Primary roadside monument / entry sign | Medium | Likely Broadalbin-Perth Jr./Sr. High School or Broadalbin-Perth High School | Unspecified | Approx. 4' x 8' face; aluminum/composite refacing or full monument rebuild | 1 | $9,700 / $19,900 / $46,300 | 45-90 | $9,700 / $19,900 / $46,300 | The district uses both "High School" and "Jr./Sr. High School" for the same 100 Bridge Street campus. This row assumes at least one primary entrance sign exists and must be reconciled. [26] |
| Exterior campus wayfinding set | Medium | Likely High School, Jr./Sr. High School, Lecture Hall, Counseling, Auditorium | Unspecified | 36" x 36" .080 aluminum directional signs on posts | 3 | $650 / $1,050 / $1,700 | 24-48 | $1,950 / $3,150 / $5,100 | Official pages explicitly use these destination names. Pricing based on campus directional-sign and post-kit pricing. [27] |
| Directional parking sign set | Low-Med | Likely High School Visitor Parking, Student Parking, Staff Parking, or BPHS Parking | Unspecified | 12" x 18" to 18" x 24" reflective aluminum on steel posts | 6 | $175 / $275 / $450 | 16-28 | $1,050 / $1,650 / $2,700 | Messages are not confirmed online, so this is an allowance row only. Unit pricing is based on stocked reflective parking signs plus installation benchmarks. [28] |
| Main lobby / reception identity sign | Medium | Likely Broadalbin-Perth High School with shield logo | Unspecified | ~24" x 48" acrylic or metal wall sign | 1 | $700 / $1,600 / $4,000 | 8-18 | $700 / $1,600 / $4,000 | Not directly shown online, but typical for a secondary-campus entrance. Local shops explicitly offer interior signs, plaques, and logo signage. [21] |
| Counseling office sign | High | Broadalbin-Perth High School Counseling Office | Unspecified | 8" x 12" to 12" x 18" office/header sign, likely ADA-compatible | 1 | $125 / $225 / $400 | 2-4 | $125 / $225 / $400 | Exact wording appears on the counseling page. Per-sign pricing based on office-sign and New York-compliant ADA sign vendors. [29] |
| Lecture hall sign | High | BPHS Lecture Hall or High School Lecture Hall | Unspecified | 8" x 12" to 18" x 24" interior plaque or wall sign | 1 | $150 / $300 / $700 | 2-4 | $150 / $300 / $700 | The lecture hall is explicitly referenced in district news and event coverage. [30] |
| Varsity baseball field sign | High | BPHS Varsity Baseball Field | Unspecified | Approx. 3' x 6' aluminum field-ID sign or scoreboard/fence panel | 1 | $900 / $1,800 / $3,500 | 6-12 | $900 / $1,800 / $3,500 | The athletics schedule uses this exact name. School-specific custom aluminum sign pricing used as basis. [31] |
| JV baseball field sign | High | BPHS JV Baseball Field | Unspecified | Approx. 3' x 6' aluminum field-ID sign or fence panel | 1 | $900 / $1,800 / $3,500 | 6-12 | $900 / $1,800 / $3,500 | The athletics schedule uses this exact name. [31] |
| Patriot Field / athletic-complex school-name panel | Low | Patriot Field or another athletic panel with school-name text, if present | Unspecified | Scoreboard header, complex identifier, or entry panel | 1 | $0 / $2,500 / $10,000 | 10-24 | $0 / $2,500 / $10,000 | Official sources confirm Patriot Field and investment in athletic facilities, but they do not confirm a school-name panel at the field. Keep as optional. [32] |
| ADA / classroom / office sign refresh allowance | Medium | Mixed room signs using High School, BPHS, or legacy sign-family naming | Unspecified | 20 mixed signs, 4" x 8" to 9" x 12", tactile/engraved/plastic/acrylic | 20 | $75 / $130 / $240 | 20-40 | $1,500 / $2,600 / $4,800 | Official pages confirm several named high-school spaces and offices. This row allows for selective replacement rather than a whole-building sign family redo. [33] |
| School-branded banners / pole banners / flags allowance | Low-Med | Likely Broadalbin-Perth, BPHS, or shield-logo graphics | Unspecified | 4 units, 16 oz vinyl or custom flag fabric | 4 | $250 / $450 / $750 | 8-20 | $1,000 / $1,800 / $3,000 | Include only school-branded banner/flag items. The U.S. and state flags in ordinary use would not normally change because of a school rename. [23] |
| Entrance / dedication plaque allowance | Low-Med | Likely school-name plaque, if present | Unspecified | Approx. 18" x 24" bronze or aluminum cast plaque | 1 | $400 / $1,200 / $3,000 | 4-8 | $400 / $1,200 / $3,000 | Not confirmed online. Keep as allowance until the field inventory is completed. [24] |

Estimated practical program total, excluding any carved-masonry discovery: $26,975 low / $54,825 mid / $116,900 high.

Possible carved-stone/brick adder, if field survey finds it: +$7,500 low / +$18,000 mid / +$35,000 high. [18]

## Timeline and procurement

A realistic schedule is about 10 to 12 weeks from final naming decision to punch list for a static-signage program. If the main monument is rebuilt, if stamped drawings are required, or if the district needs a longer board-approval cycle, the schedule can stretch to 14 to 18 weeks. This timeline is consistent with commercial sign-project workflows and with current sign-company guidance that permitting, approval, fabrication, and installation often take several weeks to a few months. [34]

gantt
    title Broadalbin-Perth High School Rename Signage Timeline
    dateFormat  YYYY-MM-DD
    axisFormat  %b %d

    section Definition
    Final school name, acronym, and sign standards :a1, 2026-05-04, 7d
    On-site inventory, measurements, and photo log :a2, after a1, 7d

    section Pricing
    Vendor RFQ issue and site walk :b1, after a2, 7d
    Quotes, alternates, and value engineering :b2, after b1, 10d
    Board / administration budget approval :b3, after b2, 7d

    section Design and approvals
    Shop drawings and artwork proofs :c1, after b3, 10d
    Permit / code review and electrical coordination :c2, after c1, 10d

    section Production
    Fabrication :d1, after c2, 15d

    section Installation
    Removal, patching, and installation :e1, after d1, 7d
    Punch list and closeout :e2, after e1, 3d

## Vendor outreach checklist

A sensible local/near-local bidder list would include Rooney Sign Company[35], entity["company","Vital Sign & Graphics","cohoes ny sign company"], Next Gen Signs[36], AJ Signs[37], and American Made Signs[38]. Their published capabilities collectively cover dimensional letters, monument signs, interior signs, plaques, digital signs, design, installation, and permitting. [39]

When you ask for quotes, send the same scope package to every bidder and insist on the same alternates. Ask these questions:

- Can you quote like-for-like replacement and an upgrade alternate for the main façade sign - non-illuminated dimensional letters vs. LED channel letters?

- Can the existing monument be refaced instead of rebuilt?

- Which signs can reuse existing posts, anchors, raceways, or electrical circuits?

- Who handles permit applications, electrical subcontracting, and any required engineered drawings?

- What assumptions are you making about substrate condition, masonry patching, lead paint, and concealed fastener damage?

- What is the warranty for finish, vinyl graphics, LEDs/power supplies, and installation workmanship?

- What equipment is required - ladders, bucket truck, crane, traffic control, stump/utility avoidance?

- What is the fabrication lead time after final artwork approval?

- Can they provide separate pricing for only confirmed rename items vs. a full sign-family refresh?

- Will they honor the district's tax-exempt purchasing process and provide unit-pricing backups?

The photo/spec package you send should include:

- Straight-on and angled photos of every sign.

- One photo showing the sign in context from the pedestrian or vehicle approach.

- Overall dimensions, letter heights, panel sizes, post spacing, and mounting height.

- Close photos of all mount points, fasteners, raceways, conduits, and any damage.

- For monument signs, a sketch showing setbacks, apron, planting bed, and any nearby utilities.

- For room and ADA signs, photos of the current plaque plus a note on whether the sign is tactile/Braille.

- Existing artwork files for the BP shield, typography, and color standards.

- The board-approved final school name, accepted abbreviations, and rules for whether "secondary campus," "high school," and "athletics" naming also change.

## Open questions and limitations

This report is intentionally conservative about unknowns.

Only one physical sign - the main exterior entrance name band - is directly visible in the attached image. The rest of the physical-sign scope is inferred from official district naming strings, which is useful for budgeting but not a substitute for a walkthrough. [40]

I did not locate an official, published online Village of Broadalbin sign-fee schedule. The permit allowances therefore use the published Town of Broadalbin fee form as a minimum public benchmark, plus reasonable local sign-permit allowances. Jurisdiction should be confirmed before the district fixes a budget. The published town documents do clearly show that alteration/removal/electrical work is permit-regulated, that the minimum fee on the town schedule is $50, and that projects above $20,000 may require stamped plans. [25]

I did not have measured drawings, existing shop drawings, electrical circuit maps, or a site utility locate. The estimate therefore assumes normal access, no hidden structural failure, no major masonry reconstruction, no underground utility conflict at monument signage, and no districtwide ADA sign-family replacement beyond the allowance row. If the field inventory finds carved masonry, scoreboard headers with the old name, or a much larger interior sign family than assumed here, the budget should be revised upward immediately.

[1] [3] [5] [6] [16] [40] https://highschool.bpcsd.org/

https://highschool.bpcsd.org/

[2] [15] [32] https://www.bpcsd.org/news/default-post-display-page/~board/news/post/capital-project-spotlight-outdoor-upgrades-1714567747357

https://www.bpcsd.org/news/default-post-display-page/~board/news/post/capital-project-spotlight-outdoor-upgrades-1714567747357

[4] [34] https://www.flexlume.com/blog/how-much-does-a-channel-letter-sign-cost

https://www.flexlume.com/blog/how-much-does-a-channel-letter-sign-cost

[7] [26] [38] https://www.bpcsd.org/

https://www.bpcsd.org/

[8] https://highschool.bpcsd.org/bookstore3

https://highschool.bpcsd.org/bookstore3

[9] https://highschool.bpcsd.org/academics/curriculum

https://highschool.bpcsd.org/academics/curriculum

[10] [37] https://resources.finalsite.net/images/v1706897982/bpcsdorg/fy3s8ekbrkfjbgqxxgim/2024HScurriculumguide.pdf

https://resources.finalsite.net/images/v1706897982/bpcsdorg/fy3s8ekbrkfjbgqxxgim/2024HScurriculumguide.pdf

[11] [13] [30] https://www.bpcsd.org/news/default-post-display-page/~board/news/post/school-budget-and-capital-project-hearing-set-for-evening-of-monday-may-13-1777641504952

https://www.bpcsd.org/news/default-post-display-page/~board/news/post/school-budget-and-capital-project-hearing-set-for-evening-of-monday-may-13-1777641504952

[12] [27] [29] [33] https://highschool.bpcsd.org/academics/counseling

https://highschool.bpcsd.org/academics/counseling

[14] [20] [31] [35] https://www.bpcsd.org/athletics

https://www.bpcsd.org/athletics

[17] https://isasign.com/sign-cost/

https://isasign.com/sign-cost/

[18] [36] https://www.artsignworks.com/products/products_services/gallery_1.html

https://www.artsignworks.com/products/products_services/gallery_1.html

[19] https://www.elementsinc.com/products/wayfinding-signs

https://www.elementsinc.com/products/wayfinding-signs

[21] https://www.impactsigns.com/product-category/business-signs/custom-office-signs/?srsltid=AfmBOoq_l18q0LcePKPc7ey1F8lkZ5Lr1CCy_nXLK6uT3-f5EgRe9d3M

https://www.impactsigns.com/product-category/business-signs/custom-office-signs/?srsltid=AfmBOoq_l18q0LcePKPc7ey1F8lkZ5Lr1CCy_nXLK6uT3-f5EgRe9d3M

[22] https://www.officesigncompany.com/door-signs/?srsltid=AfmBOopPl6pavqx86BX96vcA-h9rD3A2t4v48Rkd4FlPTD-zAwSiOfTx

https://www.officesigncompany.com/door-signs/?srsltid=AfmBOopPl6pavqx86BX96vcA-h9rD3A2t4v48Rkd4FlPTD-zAwSiOfTx

[23] https://www.schoolfix.com/custom-heavy-duty-banner-with-grommets?srsltid=AfmBOoqutqt7OenCZCkJkJZgrcF7yrwuQaRgadjAvAP_-CpNO3azXkha

https://www.schoolfix.com/custom-heavy-duty-banner-with-grommets?srsltid=AfmBOoqutqt7OenCZCkJkJZgrcF7yrwuQaRgadjAvAP_-CpNO3azXkha

[24] https://www.impactsigns.com/plaques/cast-bronze/?srsltid=AfmBOopcyKx8Jyj9oU8VPcVC-3iYNeSYnMH3u3mOLzQUbgyVN7AcIukD

https://www.impactsigns.com/plaques/cast-bronze/?srsltid=AfmBOopcyKx8Jyj9oU8VPcVC-3iYNeSYnMH3u3mOLzQUbgyVN7AcIukD

[25] https://www.townofbroadalbinny.org/BuildingPermitInfo.pdf

https://www.townofbroadalbinny.org/BuildingPermitInfo.pdf

[28] https://www.myparkingsign.com/MPS2/custom-parking-lot-directory-sign/sku-k2-3045?srsltid=AfmBOoplcFp4-gCpTrmyPldvljpmlPYcDehSZJVmJ0NuOjlC_cM69H93

https://www.myparkingsign.com/MPS2/custom-parking-lot-directory-sign/sku-k2-3045?srsltid=AfmBOoplcFp4-gCpTrmyPldvljpmlPYcDehSZJVmJ0NuOjlC_cM69H93

[39] https://business.fultonmontgomeryny.org/list/member/rooney-sign-company-220

https://business.fultonmontgomeryny.org/list/member/rooney-sign-company-220