## Timeline
Phase | Milestone | Target Date | Owner | Dependencies | Status | Notes
Confidential preparation | Confirm repo/storage and project charter | 2026-05 | Board President |  | Not Started | Starter structure created.
Policy/legal | Locate naming policy and compile counsel questions | 2026-05 |  |  | Not Started
Board alignment | Introduce preliminary framing to Board | 2026-06 |  | Policy review | Not Started
Announcement prep | Prepare for expected retirement announcement | 2026-08 |  |  | Not Started
Historical record | Conduct interviews and collect achievement evidence | 2026-09 to 2027-01 |  |  | Not Started
Ceremony | Finalize event structure | 2027-01 |  |  | Not Started
Recognition | Retirement ceremony and public announcement | 2027-03/04 |  | Legal readiness | Not Started