Project Charter - Superintendent Retirement Recognition and Naming Project

Prepared as a working project-control document for the Broadalbin-Perth Central School District Board of Education.

# Purpose

Organize a careful, dignified, legally sound, and broadly accepted recognition project for Superintendent Stephen Tomlinson, with a leading option of renaming the Junior/Senior High School as Stephen Tomlinson Junior/Senior High School.

# Working Context

Board-led process; not a public campaign at the outset.

Retirement public announcement expected around August 2026.

Retirement expected late March or early April 2027.

Recognition should avoid disrupting senior class of 2027 celebrations.

All legal, NYSED, SEDREF, district policy, signage, and records implications must be verified before public announcement.

# Early Decision Points

Whether and when to consult Stephen Tomlinson before formal action.

Whether the board should complete formal action before the ceremony, or approve a resolution of intent first.

Whether community input is legally, morally, or politically advisable before action.

Whether the school, campus, athletic facility, or another district asset is the proper naming level.

# Core Values

Institutional gratitude

Historical accuracy

Board ownership

Legal and policy discipline

Warmth without excess

Smooth transition to new name usage

# Source Notes

Starter background is drawn from the project planning prompt and Stephen Tomlinson biographical material provided for this planning effort.